## Sheet1
Task | Day 0 | Day Start | Day Completed | Day 0 | Day started | Day finished | 44317 | Start daate | duration
SUMO Development | 2021-05-01 | 2021-05-01 | 2021-05-30 | 0 | 0 | 29 |  | 2021-05-01 | 29 | 44317 | 44317 | 44346
Create bus stops | 2021-05-01 | 2021-05-01 | 2021-05-17 | 0 | 0 | 16 |  | 2021-05-01 | 16 | 44317 | 44317 | 44333
Create routes | 2021-05-01 | 2021-05-01 | 2021-05-17 | 0 | 0 | 16 |  | 2021-05-01 | 16 | 44317 | 44317 | 44333
Create simulation | 2021-05-01 | 2021-05-01 | 2021-05-23 | 0 | 0 | 22 |  | 2021-05-01 | 22 | 44317 | 44317 | 44339
Testing simulation | 2021-05-01 | 2021-05-24 | 2021-05-30 | 0 | 23 | 29 |  | 2021-05-24 | 6 | 44317 | 44340 | 44346
Python Script | 2021-05-01 | 2021-05-31 | 2021-07-11 | 0 | 30 | 71 |  | 2021-05-31 | 41 | 44317 | 44347 | 44388
Create TCP socket server | 2021-05-01 | 2021-05-31 | 2021-06-07 | 0 | 30 | 37 |  | 2021-05-31 | 7 | 44317 | 44347 | 44354
Running Simulation via python | 2021-05-01 | 2021-05-31 | 2021-06-07 | 0 | 30 | 37 |  | 2021-05-31 | 7 | 44317 | 44347 | 44354
Receiving data from the simulation | 2021-05-01 | 2021-06-08 | 2021-06-22 | 0 | 38 | 52 |  | 2021-06-08 | 14 | 44317 | 44355 | 44369
Testing python script | 2021-05-01 | 2021-06-22 | 2021-07-11 | 0 | 52 | 71 |  | 2021-06-22 | 19 | 44317 | 44369 | 44388
Application | 2021-05-01 | 2021-07-12 | 2021-09-03 | 0 | 72 | 125 |  | 2021-07-12 | 53 | 44317 | 44389 | 44442
Create the layout for the app | 2021-05-01 | 2021-07-12 | 2021-08-06 | 0 | 72 | 97 |  | 2021-07-12 | 25 | 44317 | 44389 | 44414
Create TCP client socket | 2021-05-01 | 2021-07-12 | 2021-07-16 | 0 | 72 | 76 |  | 2021-07-12 | 4 | 44317 | 44389 | 44393
Receive and display data from app | 2021-05-01 | 2021-07-16 | 2021-08-06 | 0 | 76 | 97 |  | 2021-07-16 | 21 | 44317 | 44393 | 44414
Create map on the app | 2021-05-01 | 2021-08-06 | 2021-08-27 | 0 | 97 | 118 |  | 2021-08-06 | 21 | 44317 | 44414 | 44435
Testing of the application | 2021-05-01 | 2021-08-27 | 2021-09-03 | 0 | 118 | 125 |  | 2021-08-27 | 7 | 44317 | 44435 | 44442
Testing all parts together | 2021-05-01 | 2021-09-04 | 2021-09-17 | 0 | 126 | 139 |  | 2021-09-04 | 13 | 44317 | 44443 | 44456
Formulas:
Day started = DAYS([Day Start],[Day 0])
Day finished = DAYS([Day Completed],[Day Start])+[Day started]
Start daate = [Day Start]
duration = DAYS([Day Completed],[Day Start])

## Sheet2
SUMO Development | 44317 | 29
Create bus stops | 44317 | 16
Create routes | 44317 | 16
Create simulation | 44317 | 22
Testing simulation | 44340 | 6
Python Script | 44347 | 41
Create TCP socket server | 44347 | 7
Running Simulation via python | 44347 | 7
Receiving data from the simulation | 44355 | 14
Testing python script | 44369 | 19
Application | 44389 | 53
Create the layout for the app | 44389 | 25
Create TCP client socket | 44389 | 4
Receive and display data from app | 44393 | 21
Create map on the app | 44414 | 21
Testing of the application | 44435 | 7
Testing all parts together | 44443 | 13
Creating the Poster | 44457 | 34
Completing the final report | 44457 | 34